## WFP 1
SCHOOL-BASED FEEDING PROGRAM
WORK FINANCIAL PLAN
BIGA-A ELEMENTARY SCHOOL
Region: VII
MFO/P/A/P | PERFORMANCE INDICATOR/UNIT OF MEASURE |  |  |  | PHYSICAL TARGETS |  |  |  |  | COST ASSUMPTIONS |  |  |  | FINANCIAL ESTIMATES |  |  |  |  | RESPONSIBILITY CENTER | SOURCE OF FUND | REMARKS
|  | SEP. | OCT. | NOV. | DEC. | JAN. | FEB. | MAR. | TOTAL |  | SEP. | OCT. | NOV. | DEC. | JAN. | FEB. | MAR. | TOTAL
-1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 | -22
|  | 21 | 19 | 20 | 15 | 22 | 20 | 3 | 120 |  | 21 | 19 | 20 | 15 | 22 | 20 | 3 | 120
MFO 1-A and MFO 1-B Pre-Elementary and Elementary Education Esrvices
SCHOOL-BASED FEEDING PROGRAM | *Ensure 85%-100% among target beneficiaries | [17 empty] | School | School MOOE
| *100% improvement of nutritional status of beneficiaries | [17 empty] | School | School MOOE
PER-FEEDING ACTIVITY
*Identification of severely wasted children | *pupil beneficiaries were identified | [7 empty] | 62 | [9 empty] | School | School MOOE
*Creation of BFP Core Group | *BFP Core Group was created | [7 empty] | 1 | [9 empty] | School | School MOOE
*Determine parents/volunters to assist the implementation of BFP | *Number of parents/vulonters were identified | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 60 | [9 empty] | School | School MOOE
*Finalization and approval of menu cycle for implementaion | *menu cycle was approved and identified | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | [9 empty] | School | School MOOE
*Training of parents/volunteers on food preparation | *Training of parents was conducted | 1 | 1 | [5 empty] | 2 | [9 empty] | School | School MOOE
ACTUAL FEEDING ACTIVITY
*Provision of feeding commodities | Feeding comodities were provided | [16 empty] | PhP 111,600 | School | GAA
KINDERGARTEN |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | (# of R) X(15.00)x(# of days in a month) | 4725 | 4275 | 4500 | 3375 | 4950 | 4500 | 675 | 27000 | School | GAA
Grade I |  | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 2835 | 2565 | 2700 | 2025 | 2970 | 2700 | 405 | 16200 | School | GAA
Grade II |  | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 |  | 3465 | 3135 | 3300 | 2475 | 3630 | 3300 | 495 | 19800 | School | GAA
Grade III |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 3150 | 2850 | 3000 | 2250 | 3300 | 3000 | 450 | 18000 | School | GAA
Grade IV |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 1575 | 1425 | 1500 | 1125 | 1650 | 1500 | 225 | 9000 | School | GAA
Grade V |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | 1890 | 1710 | 1800 | 1350 | 1980 | 1800 | 270 | 10800 | School | GAA
Grade VI |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | 1890 | 1710 | 1800 | 1350 | 1980 | 1800 | 270 | 10800 | School | GAA
111600
4725 | 4275 | 4500 | 3375 | 4950 | 4500 | 675 | 27000
2835 | 2565 | 2700 | 2025 | 2970 | 2700 | 405 | 16200
3465 | 3135 | 3300 | 2475 | 3630 | 3300 | 495 | 19800
3150 | 2850 | 3000 | 2250 | 3300 | 3000 | 450 | 18000
1575 | 1425 | 1500 | 1125 | 1650 | 1500 | 225 | 9000
1890 | 1710 | 1800 | 1350 | 1980 | 1800 | 270 | 10800
1890 | 1710 | 1800 | 1350 | 1980 | 1800 | 270 | 10800
111600

## WFP 2
SCHOOL-BASED FEEDING PROGRAM
WORK FINANCIAL PLAN
Region: VII
Division: NEGROS ORINTAL
District: LA LIBERTAD
school: BIGA-A ES
BEIS School ID: 120314
School Year: 2013-2014
MFO/P/A/P | PERFORMANCE INDICATOR/UNIT OF MEASURE | PHYSICAL TARGETS |  |  |  |  | COST ASSUMPTIONS | FINANCIAL ESTIMATES |  |  |  |  | RESPONSIBILITY CENTER | SOURCE OF FUND | REMARKS
|  | DEC. | JAN. | FEB. | MAR. | TOTAL |  | DEC. | JAN. | FEB. | MAR. | TOTAL
-1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16
*Preparation of food items for quotation | Food items were identified
*Grocery items, vegetable items, fish, meat, poultry and other food items
*Preparation of documents for quotation and awarding of contract to the lowest bidder/supplier | RFQ was conducted and the lowest bidder/supplier was identified
*Delivery of the goods direct to the school | Acceptance of the goods delivered
*Procurements of other food items for feeding | Delivered |  |  |  |  | 62 | 10.00/child/month | 620 | 620 | 620 | 620 | 2480 | School | HNC
*Implementation of BFP preparation and accomplishment of BFP liquidation forms and reports | Feeding of beneficiaries
*Submission of reports and papers for liquidation | *Reports on BFP were submitted and pertinent papers for BFP liquidation were submitted and liquidated
TOTAL | [11 empty] | 111600
Prepared by:
LUZVISMINDA S. GEMINA
Feeding Coordinator |  |  |  | Noted by:
GIL P. MARTINEZ
[5 empty] | school Head |  |  |  |  | Approved:
SALUSTIANO T. JIMENEZ, LL.B.
OIC, Schools Division Superintendent